## TaskList
Task List - Preview / Review
Team No. |  | 1 |  | Est. | Act. |  | Supervisor | Name
Team Member |  | Alan Koh Song Hua | AK | 3 |  |  | From | 15.Aug.2016
|  | Darryl Peter s/o Jeret | DP | 4 |  |  | To | 18.Aug.2016
|  | Chan Wen Hao Ryan | RC | 18 |  |  | Preview | 15.Aug.2016
|  | Heng Sheng Yang | SY | 18 |  |  | Review | 19.Aug.2016
No. | Title |  | Assign | Est. | Act. | Note / Comment / Issue
1 | Map(level designs, i, ) |  | SY | 15 | n/a
2 | Transitions between maps |  | RC | 3 | n/a
3 | Interactive objects |  | DP | 4 | n/a
4 | Activity feed |  | AK | 1 | 1
5 | Control edits |  | AK | 2 | 2
6 | Inventory |  | RC | 15 | n/a
7 | Collision |  | SY | 3 | 4
Total |  |  |  | 43 | 7
Comment
(Any comment for this sprint?)
Alan Koh Song Hua |  |  |  | Darryl Peter s/o Jeret
Chan Wen Hao Ryan |  |  |  | Heng Sheng Yang
Note on E9: Estimated volume of the task
Note on F9: Actual volume after work done