## TaskList
Task List - Preview / Review
Team No. |  | 1 |  | Est. | Act. |  | Supervisor | Name
Team Member |  | Alan Koh Song Hua | AK | 13 |  |  | From | 15.Aug.2016
|  | Darryl Peter s/o Jeret | DP | 5 |  |  | To | 18.Aug.2016
|  | Chan Wen Hao Ryan | RC | 21 |  |  | Preview | 15.Aug.2016
|  | Heng Sheng Yang | SY | 23 |  |  | Review | 19.Aug.2016
No. | Title |  | Assign | Est. | Act. | Note / Comment / Issue
1 | Map(level designs, i, ) |  | SY | 15 | 20
2 | Transitions between maps |  | RC | 3 | 4
3 | Chest and key |  | DP | 4 | 5
4 | Activity feed |  | AK | 10 | 5
5 | Control edits |  | AK | 2 | 2
6 | Inventory |  | RC | 15 | 10
7 | Collision |  | SY | 4 | 4
8 | Movable objects |  | SY | 4 | 6
9 | Victory screen |  | DP | 1 | 1
10 | Splashscreen |  | AK | 1 | 1
11 | Doors |  | RC | 3 | 3
Total |  |  |  | 62 | 61
Comment
(Any comment for this sprint?)
Alan Koh Song Hua |  |  |  | Darryl Peter s/o Jeret
Chan Wen Hao Ryan |  |  |  | Heng Sheng Yang
Note on E9: Estimated volume of the task
Note on F9: Actual volume after work done